## Slide 1
NextGen Fulfillment Center — Timeline Comparison
Sortable Fulfilment Strategy | April 2026
Confidential — Internal Use Only
SITE
PROGRAM TIMELINE
2025
2026
2027
2028
2029
2030
2031
Carnesville, GA
Southeast
Buckeye, AZ
West
Wallkill, NY
Northeast
Orlando, FL
Southeast
Minneapolis, MN
Upper Midwest
Denver, CO
Mountain West
Seattle, WA
Pacific NW
Design & Permits
Construction
Ph1 → Ph2
ASM Date
MILESTONE SUMMARY
Site
Site Selected
ASM
Ph1 Go-live
Duration
Carnesville, GA
May 2025
May 2026
Oct 2028
~3y 11m
Buckeye, AZ
Apr 2026
Dec 2026
Jun 2029
~3y 8m
Wallkill, NY
Oct 2025
Aug 2026
May 2030
~5y 0m
Orlando, FL
Aug 2026
Jun 2027
Mar 2030
~4y 1m
Minneapolis, MN
Aug 2026
Jun 2027
Mar 2030
~4y 1m
Denver, CO
Sep 2026
Jul 2027
Sep 2030
~4y 6m
Seattle, WA
Sep 2026
Jul 2027
Sep 2030
~4y 6m
Source: NG Scheduling.xlsx │ Dates subject to change
NextGen Fulfillment │ PMO Program Management │ Sortable Fulfilment Strategy │ CONFIDENTIAL