## Slide 1
NextGen Fulfillment Center — Timeline Comparison
Sortable Fulfilment Strategy │ April 2026
SITE
2025
2026
2027
2028
2029
2030
2031
SITE
SELECTED
ASM
PHASE 1
GO-LIVE
DURATION
Carnesville, GA
Southeast
ASM
May 2025
May 2026
Oct 2028
3Y 11m
Buckeye, AZ
West
ASM
Apr 2026
Dec 2026
Jun 2029
3y 8m
Wallkill, NY
Northeast
ASM
Oct 2025
Aug 2026
May 2030
5y 0m
Orlando, FL
Southeast
ASM
Aug 2026
Jun 2027
Mar 2030
4y 1m
Minneapolis, MN
Upper Midwest
ASM
Aug 2026
Jun 2027
Mar 2030
4y 1m
Denver, CO
Mountain West
ASM
Sep 2026
Jul 2027
Sep 2030
4y 6m
Seattle, WA
Pacific NW
ASM
Sep 2026
Jul 2027
Sep 2030
4y 6m
Design & Permits
Construction
Ph1 → Ph2
ASM Date
Source: NG Scheduling.xlsx │ Dates subject to change