## Slide 1
NextGen Fulfillment Center — Timeline Comparison
Sortable Fulfillment Strategy | April 2026
Confidential — Internal Use Only
Design & Permits
Construction
Ph1 → Ph2
ASM Date
SITE
2025
2026
2027
2028
2029
2030
2031
Carnesville, GA
Southeast
ASM
Buckeye, AZ
West
ASM
Wallkill, NY
Northeast
ASM
SITE
SITE SEL.
ASM
PH1 GO-LIVE
DUR.
Carnesville, GA
May 2025
May 2026
Oct 2028
3y 3m
Buckeye, AZ
Apr 2026
Dec 2026
Jun 2029
3y 4m
Wallkill, NY
Oct 2025
Aug 2026
May 2030
4y 5m
NextGen Fulfillment | PMO Program Management | Sortable Fulfillment Strategy | CONFIDENTIAL
Source: NG Scheduling.xlsx | Dates subject to change