## Sheet1
Node | Southeast | West | Northeast | Southeast | Upper Midwest | Mountain West | Pacific Northwest
Location | Carnesville, GA | Buckeye, AZ | Wallkill, NY | Orlando, FL | Minneapolis, MN | Denver, CO | Seattle, WA
State | GA | AZ | NY | FL | MN | CO | WA
FC Number | 4843 | TBD | 7028 | TBD | TBD | TBD | TBD
Airport Code | ATL5 | TBD | LGA1 | MCO? | MSP? | DEN? | SEA?
Site Selected | 2025-05-23 | 2026-04-02 | 2025-10-22 | 2026-08-14 | 2026-08-14 | 2026-09-18 | 2026-09-18
30% Design Complete | Carnesville, GA | 2026-06-12 | 2026-02-27 | 2026-12-11 | 2026-09-04 | 2027-01-08 | 2027-01-08
30% ROM Pricing | 2025-11-21 | 2026-07-17 | 2026-04-03 | 2027-01-29 | 2027-01-29 | 2027-02-12 | 2027-02-12
60% Design Complete | 2026-03-06 | 2026-08-21 | 2026-05-08 | 2027-03-05 | 2027-03-05 | 2027-03-19 | 2027-03-19
60% ROM Pricing | 2026-04-10 | 2026-09-25 | 2026-06-12 | 2027-04-09 | 2027-04-09 | 2027-04-23 | 2027-04-23
90% Design Complete | 2026-05-01 | 2026-10-30 | 2026-07-17 | 2027-05-14 | 2027-05-14 | 2027-05-28 | 2027-05-28
Out to Permit | 2026-05-01 | 2027-01-04 | 2026-04-20 | 2027-05-24 | 2027-05-24 | 2027-06-07 | 2027-06-07
Permit Complete | 2026-08-14 | 2027-03-19 | 2028-01-28 | 2027-12-10 | 2027-12-10 | 2028-06-09 | 2028-06-09
Construction Start | 2026-09-07 | 2027-04-19 | 2028-02-28 | 2028-01-10 | 2028-01-10 | 2028-07-10 | 2028-07-10
Construction Substantial Completion | 2028-05-05 | 2028-12-15 | 2029-10-26 | 2029-09-14 | 2029-09-14 | 2030-03-01 | 2030-03-01
Phase 1 Go-live | 2028-10-30 | 2029-06-22 | 2030-05-12 | 2030-03-11 | 2030-03-11 | 2030-09-09 | 2030-09-09
Phase 2 Go-live | 2029-05-07 | 2029-12-03 | 2030-11-04 | 2030-09-02 | 2030-09-02 | 2031-03-10 | 2031-03-10
ASM | 2026-05-20 | 2026-12-10 | 2026-08-19 | 2027-06-17 | 2027-06-17 | 2027-07-15 | 2027-07-15
Engineering Design and Install
30 % Design - ENG | 2025-09-28 | 2026-05-13 | 2026-01-28 | 2026-11-11 | 2026-08-05 | 2026-12-09 | 2026-12-09
60% Design -ENG | 2026-02-04 | 2026-07-22 | 2026-04-08 | 2027-02-03 | 2027-02-03 | 2027-02-17 | 2027-02-17
90% Design - ENG | 2026-04-01 | 2026-09-30 | 2026-06-17 | 2027-04-14 | 2027-04-14 | 2027-04-28 | 2027-04-28
KNAPP Signed SOW | 2026-05-27 | 2026-12-17 | 2026-08-26 | 2027-06-24 | 2027-06-24 | 2027-07-22 | 2027-07-22
KNAPP start of Install (Start) | 2027-06-01 | 2028-01-22 | 2028-12-11 | 2028-10-10 | 2028-10-10 | 2029-04-10 | 2029-04-10
Start of Design | 2025-07-21 | 2026-03-02 | 2025-12-01
| 1197 | 1208 | 1623
| 3.2795 | 3.3096 | 4.4466
|  | 0.030137 | 1.1671

## Start to Finish
| Southeast | West | Northeast
| Carnesville, GA | Buckeye, AZ | Wallkill, NY
Start of Design | 2025-07-21 | 2026-03-02 | 2025-12-01
60% ROM Pricing | 2026-04-10 | 2026-09-25 | 2026-07-03
ASM | 2026-05-20 | 2026-12-10 | 2026-08-19
Construction Start | 2026-09-07 | 2027-04-19 | 2028-02-28
KNAPP start of Install (Start) | 2027-06-01 | 2028-01-22 | 2028-12-11
Construction Substantial Completion | 2028-05-05 | 2028-12-15 | 2029-10-26
Phase 1 Go-live | 2028-10-30 | 2029-06-22 | 2030-05-12
Phase 2 Go-live | 2029-05-07 | 2029-12-03 | 2030-11-04
Start of Design to Phase 1 Go-Live | 3.2795 | 3.3096 | 4.4466