## Slide 1
Wallkill NextGen FC — Path to August Governance
What needs to be completed before the governance cycle starts on July 1, 2026
Inform
64 DAYS
to Governance
TODAY
Apr 28
CPC Turn-In
~Jun 15
CFO Review
~Jun 22
GOV. STARTS
Jul 1, 2026
ASM Aug 19
💰 Financials & Business Case
Due Jun 1
• True-up tariff assumptions following Supreme Court ruling & Turnberry Agreement (end of Apr)
• Finalize IRR, NPV, CapEx/OpEx ask — refresh from Nov ASM to May ASM numbers
• Lock unit mix: WFS / Sam’s / 1P split and AUR by channel
• Run IRR sensitivity scenarios; confirm 11–13% range holds
🏗 Design & Value Engineering
Due Jun 1
• Reach 60% design completion milestone
• Complete Value Engineering analysis — identify and lock savings items
• Finalize building UPH targets and automation scope with KNAPP
• Confirm Secondary ASRS aisle count, tote strategy, and sorter configuration
📍 Site, Land & Permitting
Due May 31
• Resolve outstanding wetland permits blocking land closing
• Confirm land closing timeline and downpayment schedule
• Lock site dimensions, trailer count, and dock door count for business case
• Finalize permitting path to avoid construction start delays
🤝 Incentives
Due Jun 1
• Convert informal state/county offer to formal incentive agreement
• Lock final values: sales tax exemption, tax abatement, job tax credit
• Confirm total incentive package value for business case net CapEx
• Coordinate with Real Estate and Finance to reflect in financial model
⚙️ KNAPP & Procurement
Due Jun 15
• Finalize KNAPP long-lead item orders and lock pricing
• Confirm goodwill discount amount and structure
• Lock tariff exposure on automation scope; validate against KNAPP contract
• Align on phased installation plan to support August go-live target
📋 CPC Deck, FAQs & Exec Alignment
Due Jun 22
• Update FAQ financials section (Nov ASM → May ASM numbers)
• Finalize Talking Points: 30-min ultra fast, waterfall reframe, 1P/WFS/Sam’s breakdown
• Schedule and complete CFO Review → CPC Turn-In → SteerCo
• Confirm REC/RLM sequencing ahead of July 1 governance start
⚠️ Key Risks:
Wetland permits / land closing at risk • Tariffs not yet true-up’d • Financials on Nov ASM baseline • Incentives informal • KNAPP pricing outstanding
PRIVATE AND CONFIDENTIAL