## Slide 1
Wallkill Business Case — Next Steps
Clear owners and deadlines to complete the business case before the August governance cycle
Inform
TODAY
Apr 28
May 1
Strategy + Tariffs (GT)
May 8
CapEx, Headwinds, Tariffs
GOV. STARTS
Jul 1, 2026
ASM Aug 19
Strategy
Jack Anderson + Team
Due May 1
→ Working session with Edgar, Jack & team to align on go-forward approach
→ Build the ‘no Wallkill’ case: how does the ecosystem perform without it?
→ Quantify the downside: Northeast volume loss, coverage gap, and flywheel impact
→ Answer the hard question: is not building Wallkill a viable option?
→ MTR controllership: all shipped units should count — confirm definition with Adam/Barat
Headwinds
Logan • Hari • Steve • Ary • Kourtney • Andrew
May 1 • May 8
⚠️ Tariffs (GT impact): Hari to deliver assessment by May 1
⚠️ Tariffs (KNAPP + Eng): Steve to deliver assessment by May 8
⚠️ Solar site constraints: geotech, structural/steel & wastewater — Logan/Andrew, May 8
⚠️ Energy IRR: verify business case still tracking >10% — Logan
⚠️ Transportation: operational feasibility + updated costs + layout scenarios — Ary/Kourtney/Andrew, May 8
Tailwinds
Nicole • Adam • Barat • Kodi • Steve • Kourtney
Due May 8
↑ CapEx pulse check: 30% ROM construction pricing — Kodi/Andrew, May 8
↑ Capital spend timeline: phasing, cash flow vs. plan, milestone gates — Steve/Andrew/Kourtney, May 8
↑ POD (Print on Demand): confirm viability + quantify volume, cost & margin — Nicole/Eric/Nick
↑ WFS flow shift: clarify direct-to-store volume split — Adam/Barat
↑ Feed confirmed inputs into updated IRR / NPV model once all assumptions locked
PRIVATE AND CONFIDENTIAL
Wallkill, NY NextGen FC • Business Case • Apr 28, 2026