## Budget
Carnesville
TOTAL BUDGET | Base Capex | Interest | Total Capex | Opex | Capex/Opex
LAND | 50000000 | 0 | 50000000 | 0 | 50000000
CONSTRUCTION | 539385999.8114 | 29877161.9003 | 569263161.7117 | 10114000 | 579377161.7117
ENERGY | 19293036.0119 | 0 | 19293036.0119 | 0 | 19293036.0119
INITIAL ORDER | 8352048.6 | 0 | 8352048.6 | 503312 | 8855360.6
MHE | 668151804.0468 | 38203798.7694 | 706355602.8162 | 0 | 706355602.8162
TECHNOLOGY | 41406129 | 0 | 41406129 | 0 | 41406129
TOTAL BUDGET | 1326589017.4701 | 68080960.6697 | 1394669978.1397 | 10617312 | 1405287290.1397
Wallkill
TOTAL BUDGET | Base Capex | Interest | Total Capex | Opex | Capex/Opex
LAND | 0 | 0 | 0 | 0 | 0
CONSTRUCTION | 839292340.003 | 37126987.0836 | 876419327.0866 | 16325000 | 892744327.0866
ENERGY | 26445175.3 | 0 | 26445175.3 | 150000 | 26595175.3
INITIAL ORDER | 5647534.87 | 0 | 5647534.87 | 2326513.59 | 7974048.46
MHE | 744882442.8069 | 53772204.859 | 798654647.666 | 693916.02 | 799348563.686
TECHNOLOGY | 41330766 | 0 | 41330766 | 0 | 41330766
TOTAL BUDGET | 1657598258.9799 | 90899191.9427 | 1748497450.9226 | 19495429.61 | 1767992880.5326

## CapEx Spend by FY
Carnesville
BUSINESS MODEL INPUTS |  | Total | FY26 | FY27 | FY28 | FY29 | FY30
Total Capex Budget | Capex | 1394669977.898 | 55000000 | 453729748.6078 | 575330765.2572 | 242786611.1305 | 67822852.9024
LAND | Capex | 50000000 | 0 | 50000000 |  | 0 | 0
CONSTRUCTION | Capex | 539385999.8114 | 0 | 279295199.8114 | 177336000 | 70933400 | 11821400
ENERGY | Capex | 19293036.0119 | 0 | 9027585.1919 | 10265450.82 | 0 | 0
INITIAL ORDER | Capex | 8352048.6 | 0 | 0 | 791027.67 | 7561020.93 | 0
MHE | Capex | 668151803.805 | 55000000 | 101571388.7518 | 332155825 | 123423137.1509 | 56001452.9024
TECHNOLOGY | Capex | 41406129 | 0 | 4133076.7 | 20740745.5 | 16532306.8 | 0
INTERIM INTEREST | Capex | 68080960.6697 | 0 | 9702498.1528 | 34041716.2672 | 24336746.2497 | 0
CONSTRUCTION | Capex | 29877161.9003 | 0 | 6610243.4552 | 17661237.6149 | 5605680.8302 | 0
MHE | Capex | 38203798.7694 | 0 | 3092254.6976 | 16380478.6523 | 18731065.4195 | 0
Wallkill
MODEL INPUTS |  | Total | FY26 | FY27 | FY28 | FY29 | FY30 | FY31
Total Capex Budget | Capex | 1748497450.9226 | 0 | 66128614.8688 | 226116101.0839 | 798526819.1737 | 560797493.8096 | 187827613.9293
LAND | Capex | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONSTRUCTION | Capex | 839292340.003 | 0 | 0 | 71000000 | 460255404.0018 | 230487702.0009 | 77549234.0003
ENERGY | Capex | 26445175.3 | 0 | 2644518 | 9255810 | 11900329.3 | 2644518 | 0
INITIAL ORDER | Capex | 5647534.87 | 0 | 0 | 0 | 791027.67 | 4856507.2 | 0
MHE | Capex | 744882442.8069 | 0 | 57193342.2713 | 114386684.5426 | 251290540.4451 | 228660338.1678 | 93351537.3801
TECHNOLOGY | Capex | 41330766 | 0 | 4133077 | 20665383 | 16532306 | 0 | 0
INTERIM INTEREST | Capex | 90899191.9427 | 0 | 1078838.7987 | 5404111.7706 | 28878605.8784 | 47074214.2205 | 8463421.2744
CONSTRUCTION | Capex | 37126987.0836 | 0 | 0 | 1963109.589 | 14458647.6609 | 20705229.8336
MHE | Capex | 53772204.859 | 0 | 1078838.7987 | 3441002.1816 | 14419958.2174 | 26368984.3869 | 8463421.2744

## Timeline
Program | NextGen | NextGen
Node | Southeast | Northeast
Location | Carnesville, GA | Wallkill, NY
State | GA | NY
FC Number | 4843 | 7028
Airport Code | ATL5 | LGA1
BDR Sign-off | 2025-09-23 | 2026-03-19
Design and Construction
Due Diligence: Site Selection | 2025-05-15 | 2025-11-18
Due Diligence 30% Work Ahead | 2025-05-15 | 2025-07-22
Due Diligence: 30% Design | 2025-07-17 | 2025-12-02
Due Diligence: 60% Design | 2025-11-10 | 2026-02-27
Due Diligence: 90% Design | 2025-11-10 | 2026-05-22
Due Diligence: CA Design | 2025-11-10 | 2026-08-19
Site Selected | 2025-05-23 | 2025-10-22
Start of Design | 2025-07-21 | 2025-12-01
30% Design Complete | 2025-10-28 | 2026-02-27
30% ROM Pricing | 2025-11-21 | 2026-04-03
60% Design Complete | 2026-03-06 | 2026-05-29
60% ROM Pricing | 2026-04-10 | 2026-07-03
90% Design Complete | 2026-05-01 | 2026-08-07
Out to Permit | 2026-05-11 | 2026-04-20
Permit Complete | 2026-08-14 | 2028-01-28
Construction Start | 2026-09-07 | 2028-02-28
Construction Substantial Completion | 2028-05-05 | 2029-10-26
Phase 1 Go-live | 2028-10-30 | 2030-05-12
Phase 2 Go-live | 2029-05-07 | 2030-11-04
Go-Live FY | FY29 | FY31
FY Capacity Added | FY29 | FY31
Governance
Steer Co | 2026-03-26 | 2026-07-06
Vertical Start-Up | 2026-03-19 | 2026-07-09
SCDB Turn in | 2026-03-27 | 2026-07-10
SCDB | 2026-03-30 | 2026-07-13
RLM Turn-In | 2026-03-26 | 2026-07-08
RLM | 2026-04-02 | 2026-07-14
REC Turn-In | 2026-04-10 | 2026-07-21
REC | 2026-04-15 | 2026-07-28
CFO Turn-In | 2026-04-27 | 2026-07-27
CFO Review | 2026-05-04 | 2026-08-03
CPC Turn-In | 2026-05-05 | 2026-08-04
CPC | 2026-05-11 | 2026-08-10
MSM Turn-In | 2026-05-06
MSM | 2026-05-12
ASM Turn-In | 2026-05-12 | 2026-08-11
ASM | 2026-05-20 | 2026-08-19
Engineering Design and Install
30 % Design - ENG | 2025-09-28 | 2026-01-28
60% Design -ENG | 2026-02-04 | 2026-04-29
90% Design - ENG | 2026-04-01 | 2026-07-08
KNAPP Signed SOW | 2026-05-27 | 2026-08-26
KNAPP start of Install (Start) | 2027-06-01 | 2028-12-11
Phase 1 Commissioning - (Start) | TBD | TBD
FAT, End to End Testing, Financial Validation (Start) | TBD | TBD
Additional Key Dates
Business Case Intake Open | 2026-03-16 | 2026-06-01
Business Case Intake Closed | 2026-04-06 | 2026-06-15
Business Case Complete | 2026-04-10 | 2026-07-03
Incentives Secured | TBD | TBD
REC Dry Run | 2026-04-09 | TBD
CPC Dry Run | 2026-05-01 | TBD
ASM Dry Run | TBD | TBD
Moratorium Vote | N/A | 2026-05-28
Site Selection Trip | 2025-05-23 | 2025-11-22
Talking Points & FAQ Updated | 2026-04-29 | TBD
Start of Design until Phase 1 Go-Live (Days) | 1386 | 1799
Start of Design until Phase 1 Go-Live (Years) | 3.7973 | 4.9288
Formulas:
NextGen = [NextGen, row below]-14
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure the exact date. BDR was redone after Aug ASM Rejection.
Note on C13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Partial 90% approved. Need additional 417K requires CPC approval by 5/22/26
Note on C63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Got pulled from the agenda on 4/23/26 due to a legal not having the right signature. Pending Rescheduling