## TUE FC Asset Plan SteerCo (hidden)
Fulfillment New Assets SteerCo (Tuesday's)
Date | Status | Topic | Mins | PGM POC | Lead(s) | Required Attendees: | Notes
2025-04-15 | Completed | Inform: Revised 5-yr Asset Plan and Capacity Deficits | 20 | Travis & Ellen | Centroid: Hrishi/Neeraj |  | Per alignment from Adam/Phil/CR
2025-04-15 | Completed | Post Audit results and next steps | 20 | Travis | Finance: Matt T, PK S
2025-04-22 | Completed | Grey Orange | 15 | Ellen | Xuejing Zhao
2025-04-29 | Completed | Final review of Post Audit deck; pre-V.S. 5/2 | 15 | Travis | Matt T
2025-04-29 | Completed | Prelim Eng Design Sign-off for NG Southeast | 20 | Kourtney | Lauren Siller
2025-04-29 | Completed | DFW3 / Grey Orange | 15 | Ellen | Xuejing Z, Mike S
2025-04-29 | Completed | Final Review of NextGen SE Proposal deck for DD | 30 | Kourtney | Various |  | Move to 5/1 Next Gen SteerCo
2025-04-29 | Completed | Non-Sort Purchase Strategy | 15 | Jess, Ellen | Centroid: Rohit Singhal
2025-04-29 | Completed | DFW5/PHL5 Checklist & Resource Coverage | 10 | Liz | Mike Spigoda
2025-05-06 | Completed | Revised 5 yr Asset Plan and Capacity Deficits Follow-up: Non-sort summary + overal network next steps/game plan | 30 | Travis & Ellen | Centroid: Hrishi/Rohit |  | Not covered 4.22 due to time overrun. Pushing to next week. Per 4/23 convo with Hrishi; can target 5/6 Mtg for combined sort/non-sort review + next steps
2025-05-06 | Completed | Update: Fulfillment Portfolio Prioritization "MVP" | 30 | Liz | Travis, Ellen |  | Share initial view per request last week; discuss next steps
2025-05-06 | Completed | Non-Sort CLT2 Engineering Design 30% Sign Off | 20 | Jess Stahl
2025-05-06 | Completed | IND1 (2-tier + ICC) Engineering Design | 40 | Kanistha
2025-05-27 | Completed | Decide: Prioritization Next Steps | 20 | Travis | Team
2025-05-27 | Completed | Decide: NE & W BDR Sign-off | 20 | Kourtney | Hrishi, Neeraj |  | Moved from prior meetings; need to complete. Discussed 5/27, did not finalize.
2025-05-27 | Completed | Discuss: 2-Tier Business Case and Product LOE | 30 | Ellen | Phoebe F, Manny R | Alex R, Ron J, + | Provide update post alignment from Ops, Centroid, and Finance
2025-06-10 | Completed | Decide: NE & W BDR Sign-off | 20 | Kourtney | Hrishi, Neeraj | Adam, Vik, CR, Phil, Jacob | Receieved approval sign-off with Ops offline approval
2025-06-10 | Completed | Discuss/Decide: Approach to accelerate pre-buy request to fast-follow RECC DD request | 30 | Kourtney | Kourtney | Adam, Vik, CR, Phil, Jacob | Partially Discussed: Moved to 6/17 for decsion
2025-06-17 | Completed | Energy Efficiency Projects | 30 | Travis & Ellen | Rachel Paulk | Adam, Vik, CR, Phil, Jacob | Planning for VS on 6/20, then SC DB/Eng SteerCo TBD
2025-06-17 | Off | SE Next Gen 30% Design Review | 30 | Kourtney | Nicole B | Adam, Vik, CR, Phil, Jacob | (Inform to KS on 6/20)
2025-06-17 | Completed | Discuss/Decide: Approach to accelerate pre-buy request to fast-follow REC DD request | 30 | Kourtney | Kourtney | Adam, Vik, CR, Phil, Jacob | Approved to move forward to CPC and ASM without 30% design
2025-06-17 | Completed | Inform: IND1 + Non Sort Governance Timelines | 0 | Ellen Sloneker | Ellen Sloneker
2025-06-24 | Completed | Next Gen SE Full Review: DD & Prebuy REC to ASM | 60 | Kourtney | Multiple | Adam, Vik, CR, Phil, Jacob
2025-06-24 | Completed | Review Non-Sort and IND1 (2-tier + ICC) CPC Deck | 30 | Ellen Sloneker | Multiple | Adam, Vik, CR, Phil, Jacob, Ameya, Hrishi
2025-07-09 | Completed | IND1 - Two-Tier + ICC Symbotic Engineering Design - Preliminary Review _ Sign Off | 20 | Kanistha Coombs | Joaquin Diaz Martin | Ada Dunbar, Mike Spigoda Karen Slatton
2025-07-09 | Completed | West Next Gen: Site Selection | 20 | Kourtney |  | Ada Dunbar, Mike Spigoda Karen Slatton | Vantage was approved to move forward to Karisa
2025-07-09 | Completed | SMF2 - Budget Deep Dive and Ad Hoc Requests | 30 | Liz Glenn | Multiple | Ada Dunbar, Mike Spigoda Karen Slatton
2025-07-15 | Completed | SMF2 Budget Review | 30 | Liz Glenn | Liz | Adam, Vik, CR, Phil, Jacob | Follow up from 7/11.
2025-08-12 | TBD | Decide: NE, W, & SE: DD Prebuy, and Land Bank Proposal approval prior to VS Review | 75 | Kourtney | Kourtney
2025-08-19 | Completed | SMF2 Budget Update August | 15 | Liz | Liz G | Adam, Vik, CR, Phil, Jacob, Brian | Inform : Status of all active projects budgets. Follow up on SMF2 open actions
2025-08-26 | Completed | Decide: IND1 2Tier Operations and Review | 40 | Kanistha | Joaquin | Adam, Vik, CR, Phil, Jacob
2025-08-05 | Completed | Inform: NE Site Selection - Risk | 30 | Kourtney | Allison | Adam, Vik, CR, Phil, Jacob, Brian | Going to VS on 8/8
2025-08-05 | Completed | Inform: West Site Section- Risk | 30 | Kourtney | Allison | Adam, Vik, CR, Phil, Jacob, Brian | Going to VS on 8/8
2025-08-05 | Completed | Review: SE Next Gen CPC Feedback Review | 60 | Kourtney | Nicole B | Adam, Vik, CR, Phil, Jacob, Brian
2025-07-17 | Completed | ORD1 Mezzanine Follow-up | 15 | Liz Glenn | Tabitha M / MaryEllen K | Adam, Vik, Jacob, ...
9.2.2025 | Scheduled | Decide: Site Selection NE NonSort(Hartford, CT and Central PA. Align: FY29 + FY30 Non-Sort Asset Strategy | 45 | Ellen Sloneker | Rodrigo, Allison , Joaquin | Adam, Vik, CR, Phil, Jacob, Brian, Bradon Massey | Going to VS on 8/8
7/29/2025 Move to 7/30 | Completed | Discuss: NE/W Status - Discuss risks to plan and align on expectations | 30 | Kourtney | Kourtney | VPs | This was Pre-read only
7/29/2025 Move to 7/30 | Completed | Decide: SE NG 30% Design Buidling Infrastructure | 30 | Kourtney | Nicole B | Adam, Vik, CR, Phil, Jacob, Brian | Building Infrastructure – 65’ Clear, Building Size for Offline Area, Mezzanine Pre-Build for Flexibility IP Assumptions to Enable Handoff to Construction
7/29/2025 Move to 7/30 | Completed | Decide: IP BDR Sign-off | 30 | Ellen | Vijay | Adam, Vik, CR, Phil, Jacob, Brian | Decide: BRD Leadership Sign-off going to VS 8/8
2025-08-14 | Completed | SMF2 Next Gen Totes | 20 | Liz | Mahil and David D | Adam, Vik, CR, Phil, Jacob, Brian | Review the tote selection for SMF2
9.2.2025 | Scheduled | Update: SE Next Gen - White Paper/PPT Update | 45 | Kourtney | Kourtney | Adam, Vik, CR, Phil, Jacob, Brian
TBD | TBD | Decide: DFW5/PHL5 BDR sign-off | 20 | Liz | Neeraj, Pradeep | Adam, Vik, CR, Phil, Jacob | BDR provided to Eng on 4/21. Eng has stopped review due to direction; if directed to restart will need ~1-1.5 weeks for Eng review and then ~1 week for Cen revisions.
TBD | TBD | Inform: Peak Shaving Follow-up | 30 | N/A | Adam, Hrishi, Vik | Jack A, (Merch?) | Dropped from 5/27 per Hrishi
2025-09-09 | Completed | Decide: West Site Selection | 30 | Kourtney | Kourtney | Adam, Vik
2025-09-16 | Scheduled | Decide: NG Norheast and West Prelim Eng Design Sign-off | 30 | Kourtney | Nicole B | Adam, Vik, CR, Phil, Jacob, Brian
2025-09-16 | Scheduled | Decide: NG Nov Capital Cycle Approval | 60 | Kourtney | Team | Adam, Vik, CR, Phil, Jacob, Brian
2025-09-23 | Scheduled | Decide: Non-Sort ¦¦ BDL DD + Central PA Site Selection | 20 | Ellen Sloneker |  |  | VS on 9/26
2025-09-23 | Scheduled | Decide: LAX2 ICC Expansion FY27 | 20 | Kanistha Coombs | Team | Vik, Phil, Adam, Ameya, Akash, Joaquin, MaryEllen, Kyle Caryle | VS on 9/26 a) Review design and operational modifications within LAX2 to partially support LRP need for next year b) Review options recommended (with associated pros and cons of each option) to help bridge the capacity need for FY27 and FY28 c) Future roadmap for ICCs needed based on current LRP projections.
2025-09-23 | Scheduled | Inform: IND1 2 Tier Decision Board Pre-Review | 30 | Kanistha Coombs | Team | Vik, Phil, Adam, Ameya, Akash, Joaquin, MaryEllen | VS on 9/26 Review updated deck with Karisa'a feedback on: a) a clear outline of the process flow through the current engineering design b) updated business case outlining how seller fees are being subsidised
2025-09-23 | Scheduled | Decide: Next Gen SE Land Purchase and Design Fees | 30 | Kourtney Miller | Team | Vik, Phil, Adam, Ameya, Akash, Joaquin, MaryEllen | VS on 9/26
2025-09-30 | Scheduled | Decide: LAX2 ICC Expansion FY27 | 30 | Kanistha Coombs | Joaquin Diaz Martin, Alayah Silas, Manny Rodriguez | Vik, Phil, Adam, Hrishi | Review updates on engineering design from 9/23 Asset SteerCo
2025-10-07 | Scheduled | PHL5/DFW5 Buisness Case Discussion | 30 | Liz Glenn | Nicole B, Neerja, Luke P | Vik, Phil, Adam, Hrishi | Discuss the PHL5/DFW5 buisness case and next steps
2025-09-30 |  | Decide: DFW5/PHL5 Path Forward | 15 | Liz Glenn | Nicole Blyth, Dave Hall | Mike Spigoda, Phil, Adam, Hrishi, Jacob Shub, Dave Hall | What needs to be true to hit a December governance timeline and FY27 pre-peak go live.
2025-09-30 |  | Align: Supply Chain Decision board feedback and next steps (NextGen + IND1-Two Tier + ICC) | 20 | Kanistha Coombs and Kourtney Miller | Joaquin Diaz Martin, Nicole Blyth, Manny Rodriguez | Mike Spigoda, Phil, Adam, Hrishi, Jacob Shub, Barat Smith, Mitch Fevold | Debrief and align next steps following SCDB
2025-10-07 | Scheduled | Non-Sort Optimization | 30 | Scott Smith |  | Vik, Phil, Adam, Hrishi
2025-10-07 | Scheduled | LAX2 ICC Expansion | 30 | Kanistha Coombs
2025-10-14 | Scheduled | IND1 FAQ Review | 30 | Kanistha Coombs | Hrishi, Fede, Noah, Manny, Mo, Vamsi | Vik, Phil, Jacob, Alex, Adam
2025-10-14 | Scheduled | NE & W CapEx | 30 | Kourtney Miller | Nicole B, Kodi, Neeraj, Allison, Zach | Adam, Vik, CR, Phil, Jacob, Brian
2025-10-21 | Scheduled | DFW5/PHL5 Expansions | Pre-Read | Liz Glenn | Luke Pullock/Nicole B |  | Buisness case update
2025-10-21 | Scheduled | SMF2 Yard Truck | 10 | Maryellen /Liz Glenn | Adam, Barat
2025-10-28 | Scheduled | NE & W CapEx | 15 | Kourtney Miller | Nicole B, Kodi, Neeraj, Allison, Zach | Adam, Mike S, CR, Phil, Jacob, Karen
2025-10-21 | Tentative | LAX2 Design Sign off | 30 | Kanistha Coombs | Noah | Adam, Vik, CR, Phil, Jacob, Brian
2025-10-21 | Scheduled | IP Design 60% Sign off | 30 | Ellen | Nicole B | Adam, Vik, CR, Phil, Jacob, Brian
2025-10-21 | Scheduled | Non-Sort Asset FY29/FY30 - BDL, CVG, Central PA (x2) | 30 | Ellen Sloneker
2025-10-28 | Scheduled | DFW5/PHL5 Expansions | 25 | Liz Glenn | Nicole B & Luke Polluck | Adam,Mike, CR, Phil, Jacob, Karen
2025-10-21 | Scheduled | Pre-Read PHX2 90% | Pre-Read | Scott Smith | Wil Elshoff, Scott Smith | Adam, Vik, CR, Phil, Jacob, Brian
2025-10-28 | Scheduled | WFS RC Intergration | 25 | Scott Smith | Scott Smith, Aditya Afle, Christy Olsen, Bucky Bailess | Adam, Sylvester, Phil, Jacob, Karen
2025-10-28 | Scheduled | LAX2 Design Sign off | 25 | Kanistha Coombs | Noah Jackson & Mike Spigoda | Adam, Mike S, CR, Phil, Jacob, Karen
2025-11-04 | Complete | LAX2 Strategy and BC Review | 25 | Kanistha Coombs | Federico Laino, Manny Rodriguez cc: Akash Agrawal | Adam, Mike S., Phil, Jacob
2025-11-04 | Complete | LAX Standalone ICC BDR Review | 25 | Kanistha Coombs | Federico Laino, Hrishi Badve | Adam, CR, Phil
2025-11-11 | Scheduled | DFW5/ PHL5 Expansions - DD Fund ask + 60% design sign off | 30 | Liz Glenn | Liz Glenn | Adam, Mike S., Phil, Jacob | Automation Counsel 11/13
2025-11-04 | Complete | BRD and ENG Concept Design FY29 Nonsort CVG2, PHL6, BDL1 | 40 | Ellen | Akkshit, Joaquin Diaz | Adam, Mike S., Phil, Jacob
2025-11-11 | Scheduled | SMF2 Budget Update- PreRead Only | 0 | Liz Glenn | Liz , Kodi
2025-11-11 | Scheduled | FL9 Lease Renewal | 20 | Ellen Sloneker | Allison Coontz, Manny Rodriguez, Loren Beightol
2025-11-11 | Scheduled | LAX2 Budget + Strategy | 40 | Kanistha
2025-11-18 | Scheduled | Pre-Read FL9 Lease Renewal | 0 | Ellen | -- | --
2025-11-25 | Scheduled | PHL1 IP Phase 2 Design | 30 | Nicole Blythe | Nicole Blythe | Adam Dunbar, Mike Spigoda, Karen Slatton, Phil Herr, Jacob Shub
2025-11-18 | Scheduled | New Next Gen (Closed Session) | 30 | Kourtney Miller | Kourtney Miller | Adam Dunbar, Mike Spigoda, Karen Slatton, Phil Herr, Jacob Shub , PK, Brandon
2025-12-02 | Completed | LAX1 Sorter | 30 | Ellen Sloneker
TBD | Not Scheduled | Non-Sort EV Yard Truck Review | 15 | Scott Smith | Scott Smith, Wil Elshoff, Devin Pitts | Adam Dunbar, Mike Spigoda, Karen Slatton, Phil Herr, Dave Hall
2025-12-16 | Scheduled | Atlas Roadmap Discusson : Closed Session | 30 | Meghan
2025-12-09 | Complete | Peak Pop Up Discussion | 30 | Liz Glenn
2026-01-06 | Scheduled | Expansions : RRF Funds Review | 30 | Liz Glenn | Luke
2025-12-09 | Complete | SMF2 Budget | 15 | Liz Glenn
2025-12-09 | Complete | LAX2 ICC Expansion : CPC Preview | 10 | Kanistha |  | Adam Dunbar, Mike Spigoda, Karen Slatton, Phil Herr, Jacob Shub
2025-12-16 | Scheduled | NE & W CapEx Pulse Check (Closed Session) | 60 | Kourtney Miller | Andrew & Kodi | Adam Dunbar, Mike Spigoda, Karen Slatton, Phil Herr, Jacob Shub
2025-01-06 | Scheduled | Peak Pop Up SCDB | 30 | Liz Glenn |  |  | SCDB on 1/12
2025-12-16 | Scheduled | IND1 Opertaionl Update | 60 | Kanistha
*-

## NG Scheduling
WW | Program | Status | Forum | Governance Date | Topic | Turn-in WW | Turn-in Date | Turn-in Time | Mins | Presenter | Submitter | Purpose | Decision & Outcome | Presentation Link | Decision Owners & Approvers | WW Turn-in Date
FY26 | NextGen | Complete | SteerCo | 2026-01-22 | Pivot from Las Vegas to Phoenix | FY26 | 2026-01-21 | 15:00 | 30 | Kourtney Miller | Kourtney Miller | Approved | Aligned to Pivot to Phoenix
FY26 | NextGen | Complete | SteerCo | 2026-01-22 | Las Vegas Land Bank | FY26 | 2026-01-21 | 15:00 | 30 | Kourtney Miller | Kourtney Miller | Approved |  |  |  | 2026-01-21
FY26 | NextGen | Complete | SteerCo | 2026-01-22 | Douglas PSA | FY26 | 2026-01-21 | 15:00 | 30 | Kourtney Miller | Kourtney Miller | Not Approved | Stop due diligence for Douglas |  |  | 2026-01-21
FY26 | NextGen | Complete | Vertical Start-up | 2026-01-23 | Pivot from Las Vegas to Phoenix | FY26 | 2026-01-22 | 15:00 | 30 | Vijay Manoharan | Kourtney Miller | Inform | Aligned to Pivot to Phoenix |  |  | 2026-01-22
1 | NextGen | Complete | Mechanisms | 2026-02-03 | Pivot from Las Vegas to Phoenix | 1 | 2026-02-02 | 15:00 | 30 | Ellen Sloneker | Kourtney Miller | Approved | Aligned to Pivot to Phoenix |  |  | 2026-02-02
1 | NextGen | Complete | Mechanisms | 2026-02-03 | Las Vegas Land Bank | 1 | 2026-02-02 | 15:00 | 30 | Ellen Sloneker | Kourtney Miller | Move Forward |  |  |  | 2026-02-02
1 | NextGen | Complete | Mechanisms | 2026-02-03 | 30-60% DD Request REC request for Wallkill and Buckeye | 1 | 2026-02-02 | 15:00 | 30 | Ellen Sloneker | Kourtney Miller | Not Improved | Rob's wants a review of the Depot and NextGen Ecosystem |  |  | 2026-02-02
1 | NextGen | Complete | Mechanisms | 2026-02-03 | $1M DD for MCO, SEA, DEN, MSP | 1 | 2026-02-02 | 15:00 | 30 | Ellen Sloneker | Kourtney Miller | Not Improved | Rob's wants a review of the Depot and NextGen Ecosystem |  |  | 2026-02-02
3 | NextGen | Complete | SteerCo | 2026-02-20 | Carnesville CapEx Reduction - MHE Value Engineering | 3 | 2026-02-19 | 15:00 | 30 | Nicole Blythe | Kourtney Miller | Approved | Approve to implement VE for all NextGen's |  |  | 2026-02-19
3 | NextGen | Complete | SteerCo | 2026-02-20 | Sortable SKU Definition < 1.6 to 1.2 | 3 | 2026-02-19 | 15:00 | 30 | Nicole Blythe | Kourtney Miller | Not Approved | Pause active work for 1.2 Units Cube | 26_02_20 Carnesville CapEx Reduction Slides-SteerCo.pdf |  | 2026-02-19
4 | NextGen | Complete | SteerCo | 2026-02-26 | Carnesville Business Case | 4 | 2026-02-25 | 15:00 | 30 | Matt Termeer | Kourtney Miller | Inform |  |  |  | 2026-02-25
4 | NextGen | Complete | SteerCo | 2026-02-26 | Increase IP from 60% to 80% | 4 | 2026-02-25 | 15:00 | 30 | Hrishi Badve | Kourtney Miller | Approved |  | 26_02_26 SteerCo Carnesville BC_IP Increase Yard Trucks.pptx |  | 2026-02-25
4 | NextGen | Complete | SteerCo | 2026-02-26 | EV Yard Trucks | 4 | 2026-02-25 | 15:00 | 30 | Brook Weeks | Kourtney Miller | Approved |  | 26_02_26 SteerCo Carnesville BC_IP Increase Yard Trucks.pptx |  | 2026-02-25
4 | NextGen | Complete | Rob's 1:1 w/Kieran | 2026-02-27 | 30-60% DD Request REC request for Wallkill and Buckeye | 4 | 2026-02-26 | 15:00 | 30 | Ellen Sloneker | Ellen Sloneker | Approved |  |  |  | 2026-02-26
4 | NextGen | Complete | Rob's 1:1 w/Kieran | 2026-02-27 | NextGen vs Depot Strategy | 4 | 2026-02-26 | 15:00 | 30 | Jack Anderson | Ellen Sloneker | Aligned |  |  |  | 2026-02-26
5 | NextGen | Complete | SteerCo | 2026-03-02 | Buckeye Site Selection | 5 | 2026-03-01 | 15:00 | 30 | Allison Coontz | Kourtney Miller | Move Forward |  |  |  | 2026-03-01
5 | NextGen | Complete | Vertical Start-up | 2026-03-02 | Buckeye Site Selection | 5 | 2026-03-01 | 15:00 | 30 | Allison Coontz | Kourtney Miller | No |  |  |  | 2026-03-01
5 | NextGen | Complete | SteerCo | 2026-03-05 | Impact to Increase in IP Increase | 5 | 2026-03-04 | 15:00 | 30 | Nicole Blythe | Kourtney Miller | Inform |  | 26_03_05 SteerCo IP Moved to 80%_Wallkill Political Update & Business Case.pptx |  | 2026-03-04
5 | NextGen | Complete | SteerCo | 2026-03-05 | IP Limit | 5 | 2026-03-04 | 15:00 | 30 | Hrishi Badve | Kourtney Miller | Inform |  | 26_03_05 SteerCo IP Moved to 80%_Wallkill Political Update & Business Case.pptx |  | 2026-03-04
5 | NextGen | Complete | SteerCo | 2026-03-05 | IP Increase Impact to Business Case | 5 | 2026-03-04 | 15:00 | 30 | Matt Termeer | Kourtney Miller | Inform | Approve to implement VE for all NextGen's | 26_03_05 SteerCo IP Moved to 80%_Wallkill Political Update & Business Case.pptx |  | 2026-03-04
5 | NextGen | Complete | SteerCo | 2026-03-05 | Wallkill Pollical Headwinds | 5 | 2026-03-04 | 15:00 | 30 | Kourtney Miller | Kourtney Miller | Inform |  | 26_03_05 SteerCo IP Moved to 80%_Wallkill Political Update & Business Case.pptx
6 | NextGen | Complete | SteerCo | 2026-03-12 | Increasing Energy CapEx by $5.1M | 6 | 2026-03-11 | 15:00 | 30 | Zach Freeze | Kourtney Miller | Approved | Approved Increase CapEx for Energy | 26_03_12 SteerCo Energy CapEx Increase.pptx
6 | NextGen | Complete | SteerCo | 2026-03-12 | Buckeye BDR Sign-off | 6 | 2026-03-11 | 15:00 | 30 | Hrishi Badve | Kourtney Miller | Not Approved | Additional follow-up Required | 26_03_12 SteerCo.pptx
6 | NextGen | Complete | SteerCo | 2026-03-12 | Carnesville Business Case Inputs | 6 | 2026-03-11 | 15:00 | 30 | Matt Termeer | Kourtney Miller | Inform |  | 26_03_12 SteerCo.pptx
6 | NextGen | Complete | SteerCo | 2026-03-12 | Carnesville May ASM Content Alignment | 6 | 2026-03-11 | 15:00 | 30 | Kourtney Miller | Kourtney Miller | Inform |  | 26_03_12 SteerCo.pptx
7 | NextGen | Complete | SteerCo | 2026-03-19 | Wallkill Timeline push from Nov FY30 to May FY31 | 7 | 2026-03-18 | 15:00 | 30 | Karen Slatton | Kourtney Miller | Approved |  | 26_03_19 SteerCo BDR Buckeye & Wallkill_ Wallkill Timeline.pptx
7 | NextGen | Complete | SteerCo | 2026-03-19 | Buckeye BDR Sign-off | 7 | 2026-03-18 | 15:00 | 30 | Vijay Manoharan | Kourtney Miller | Approved | Buckeye BDR Approved | 26_03_19 SteerCo BDR Buckeye & Wallkill_ Wallkill Timeline.pptx
7 | NextGen | Complete | SteerCo | 2026-03-19 | Wallkill BDR Sign-off | 7 | 2026-03-18 | 15:00 | 30 | Vijay Manoharan | Kourtney Miller | Approved | Wallkill BRR Approved | 26_03_19 SteerCo BDR Buckeye & Wallkill_ Wallkill Timeline.pptx
7 | NextGen | Complete | Vertical Start-up | 2026-03-19 | Carnesville Full Capital Ask | 7 | 2026-03-18 | 15:00 | 30 | Team | Kourtney Miller | Decision
9 | NextGen | Complete | Vertical Start-up | 2026-04-02 | Wallkill Business Case | 9 | 2026-04-01 | 12:00 | 15 | Matt Termeer | Matt Termeer | Inform |  | Wallkill VS Update | Karisa Sprague, Adam Dunbar, Barat Smith
9 | NextGen | Complete | Vertical Start-up | 2026-04-02 | Wallkill Status Update | 9 | 2026-04-01 | 12:00 | 15 | Kodi Pratt | Kodi Pratt | Inform |  | Wallkill VS Update | Greg Nunn, Jason Klipa
9 | NextGen | Complete | Vertical Start-up | 2026-04-02 | Wallkill Timeline Update | 9 | 2026-04-01 | 12:00 | 15 | Kodi Pratt | Kodi Pratt | Inform |  | Wallkill VS Update | Greg Nunn, Jason Klipa
9 | NextGen | Complete | Vertical Start-up | 2026-04-02 | Wallkill status update with pollical risk | 9 | 2026-04-01 | 15:00 | 30 | Kodi Pratt | Kourtney Miller | Inform
9 | NextGen | Complete | Vertical Start-up | 2026-04-02 | Wallkill Go Live date push from Nov to May | 9 | 2026-04-01 | 15:00 | 30 | Kodi Pratt | Kourtney Miller | Inform
9 | NextGen | Complete | Vertical Start-up | 2026-04-02 | Wallkill business case | 9 | 2026-04-01 | 15:00 | 30 | Matt Termeer | Kourtney Miller | Inform
9 | NextGen | Complete | FOX | 2026-04-02 | Fulfillment Ecosystem | 9 | 2026-04-01 | 15:00 | 60 | Jack Anderson, Adam Dunbar |  | Inform | Carnesville Pre-socialization | Carnesville May ASM | Leah Platz, Kyle Carlyle, Mike Walden
9 | NextGen | Complete | NextGen SteerCo | 2026-04-03 | Carnesville Maintenance Strategy | 9 | 2026-04-02 | 15:00 | 15 | Nicole Byth | Nicole Byth | Decide | Add Project Antelope to Carnesville Business Case | SteerCo 4/3 | Kelly Boyle, Micah Baldwin, Joel Beckwith, Fred Gulley
9 | NextGen | Complete | NextGen SteerCo | 2026-04-03 | Cost to Server | 9 | 2026-04-02 | 15:00 | 15 | Nicole Byth | Nicole Byth | Discuss |  | SteerCo 4/4
9 | NextGen | Complete | Offline | 2026-04-03 | REC Dry Run | 9 | 2026-04-03 | N/A | 60 | Ellen Sloneker | Kourtney Miller | Prepare |  | Carnesville May ASM | Karisa Sprague, Adam Dunbar, Barat Smith
9 | NextGen | Complete | SteerCo | 2026-04-03 | Adding Project Antelope to Carnesville Business Case | 9 | 2026-04-02 | 15:00 | 30 | Nicole Blythe | Kourtney Miller | Approved | Approved to adding Project Antelope to all NextGen Business Cases | 26_04_02 SteerCo Cost to Server Carnesville Maintenance Strategy.pptx
9 | NextGen | Complete | SteerCo | 2026-04-03 | Cost to Serve Alignment | 9 | 2026-04-02 | 15:00 | 30 | Nicole Blythe | Kourtney Miller | Approved | Proceed with Option 1 | 26_04_02 SteerCo Cost to Server Carnesville Maintenance Strategy.pptx
10 | NextGen | Complete | Mechanisms | 2026-04-07 | DD for MCO, MSP, DEN, SEA | 10 | 2026-04-06 | 12:00 |  | Ellen Sloneker | Ellen Sloneker | Decide |  | Rob Mechanism Update
10 | NextGen | Complete | Offline | 2026-04-07 | Fulfillment Ecosystem, Cost, & Value Engineering w/ Rob Montgomery | 10 | 2026-04-06 | 15:00 | 60 | Jack Anderson, Karisa Sprague, Adam Dunbar |  | Inform | Carnesville Pre-socialization | Carnesville May ASM | Rob Montgomery
10 | NextGen | Complete | Offline | 2026-04-09 | REC Dry Run | 10 | 2026-04-08 | N/A | 60 | Ellen Sloneker | Kourtney Miller | Prepare |  | Carnesville May ASM | Karisa Sprague, Adam Dunbar, Barat Smith
10 | NextGen | Complete | NextGen SteerCo | 2026-04-09 | Socialization Strategy | 10 | 2026-04-08 | 15:00 | 30 | Kourtney Miller | Kourtney Miller | Prepare |  | SteerCo 4/9
10 | NextGen | Complete | Rob's 1:1 w/Kieran | 2026-04-10 | Carnesville Full Capital Ask | 10 | 2026-04-09 | 12:00 | 30 | Adam Dunbar | Kourtney Miller | Decide | Full approval for Carnesville | Carnesville May ASM | This was cancelled since the meeting was moved post REC
11 | NextGen | Complete | SteerCo | 2026-04-13 | NextGen + Non-sort Campus Approach (MCO, MSP, DEN, SEA) | 11 | 2026-04-13 | 12:00 | 40 | Kourtney Miller | Kourtney Miller | Decide | Requirements for Campus | 26_04_13 SteerCo NG & NS Campus.pptx | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
11 | NextGen | Complete | Offline | 2026-04-13 | Carnesville Pre-socialization + MSM / Julie Barber | 11 | 2026-04-12 | 15:00 | 60 | Jack Anderson, Karisa Sprague, Adam Dunbar, Leah Platz |  | Inform | Carnesville Pre-socialization | Carnesville May ASM | Julie Barber
11 | NextGen | Complete | REC | 2026-04-15 | Carnesville Full Capital Ask | 10 | 2026-04-10 | 15:00 | 30 | Karisa Sprague | Kourtney Miller | Approved | Move forward to CPC | Carnesville May ASM | Rob Montgomery, Karisa Sprague, Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton, PK Sabherwal, Matt Termeer, Nicole Blyth, Ellen Sloneker, Karen Slatton
11 | NextGen | Complete | NextGen SteerCo | 2026-04-17 | BDR for MCO | 11 | 2026-04-16 | 15:00 | 30 | Vijay Manoharan | Vijay Manoharan | Approved | BDR Approved for MCO | SteerCo 4/17 | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
11 | NextGen | Complete | NextGen SteerCo | 2026-04-17 | Buckeye: Transportation & Solar Land Requirements | 11 | 2026-04-16 | 15:00 | 30 | Ary Neuwirth & Logan Jones | Ary Neuwirth & Logan Jones | Follow-up | Need Rob's feedback. Follow up required | SteerCo 4/17 | Alesha Murcia, Ary Neuwirth, Zack Freeze
12 | NextGen | Complete | Offline | 2026-04-21 | Carnesville Pre-socialization + MSM / Dave Guggina | 12 | 2026-04-20 | 12:00 | 30 | Adam Dunbar | Kourtney Miller | Inform | Pre-CPC feedback | Carnesville May ASM | Dave Guggina, Karisa Sprague, Adam Dunbar, Jacob Shub, John Clinton, Vik Gopalakrishnan, Ellen Sloneker
12 | NextGen | Complete | Offline | 2026-04-21 | Carnesville Pre-socialization / Tim Skinner | 12 | 2026-04-20 | 15:00 | 60 | Jack Anderson, Karisa Sprague, Adam Dunbar, Mike Walden |  | Inform | Carnesville Pre-socialization | Carnesville May ASM | Tim Skinner
12 | NextGen | Complete | NextGen SteerCo | 2026-04-23 | BDR for MSP, DEN, SEA | 12 | 2026-04-22 | 15:00 | 30 | Vijay Manoharan | Vijay Manoharan | Decide | Not approved - Scheduling follow up | SteerCo 4/23 | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
12 | NextGen | Complete | SteerCo | 2026-04-23 | Follow up Buckeye: Transportation & Solar Land Requirements | 12 | 2026-04-22 | 16:00 | 15 | Ary Neuwirth & Logan Jones | Ary Neuwirth & Logan Jones | Decide | Approved | SteerCo 4/23
12 | NextGen | Complete | Offline | 2026-04-23 | Carnesville Pre-socialization + MSM w/ Seth Dallaire & Manish Joneja | 12 | 2026-04-22 | 15:00 | 60 | Jack Anderson, Karisa Sprague, Adam Dunbar, Kyle Carlyle |  | Inform | Carnesville Pre-socialization | Carnesville May ASM | Seth Dallaire & Manish Joneja
12 | NextGen | Complete | Offline | 2026-04-24 | Buckeye Transportation Land Requirements w/ Rob Montgomery | 12 | 2026-04-23 | 16:00 | 60 | Ellen Sloneker | Ellen Sloneker | Decide | Pursue all 63 areas for Buckeye | 26_04_24 Buckeye Land Purchase Alignment.pptx | Rob Montgomery and Ryan McDaniels
13 | NextGen | Complete | Offline | 2026-04-27 | Carnesville Pre-socialization + MSM / Todd Sears | 13 | 2026-04-26 | 15:00 | 60 | Rob Montgomery, John Clinton, PK Sabherwal, Matt Termeer |  | Inform | Carnesville Pre-socialization | Carnesville May ASM | Todd Sears
13 | NextGen | Complete | SteerCo | 2026-04-27 | Wallkill Business Case Inputs - Action to Improve IRR | 12 | 2026-04-24 | 16:00 | 60 | Kourtney Miller | Kourtney Miller | Inform |  | 26_04_27 Wallkill IRR Deep Dive.pptx | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
13 | NextGen | Complete | NextGen SteerCo | 2026-04-30 | Burn Testing for NextGen | 13 | 2026-04-29 | 16:00 | 15 | Kodi Pratt | Kodi Pratt | Decide | Approved. Matt Termeer finding funding | 26_04_30 SteerCo.pptx | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
13 | NextGen | Complete | NextGen SteerCo | 2026-04-30 | Wallkill Business Case | 13 | 2026-04-29 | 4:00 | 45 | Kourtney Miller | Kourtney Miller | Inform |  | 26_04_30 SteerCo.pptx | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
13 | NextGen | Complete | NextGen SteerCo | 2026-05-01 | Carnesville MSM Dry Run | 13 | 2026-04-29 | 16:00 | 60 | Karisa Sprague | Kourtney Miller | Prepare |  | Carnesville May ASM | Karisa Sprague, Adam Dunbar, John Clinton
13 | NextGen | Complete | Offline | 2026-05-01 | Carnesville Pre-socialization + MSM w/ Tracy Poulliot , Camilo Canedo, Dan Fleming | 13 | 2026-04-30 | 15:00 | 60 | Jack Anderson, Karisa Sprague, Adam Dunbar, Mike Walden |  | Inform | Carnesville Pre-socialization | Carnesville May ASM | Tracy Poulliot , Camilo Canedo, Dan Fleming
14 | NextGen | Complete | CFO Review | 2026-05-04 | Carnesville Full Capital Ask | 13 | 2026-04-27 | 12:00 | 30 | John Clinton, PK Sabherwal, Matt Termeer | Kourtney Miller | Decide | Full approval for Carnesville | Carnesville May ASM | Todd Sears
14 | NextGen | Complete | NextGen SteerCo | 2026-05-04 | Van Delivery Requirements / Flow | 13 | 2026-05-01 | 16:00 | 20 | Advaith Venkataraman | Advaith Venkataraman | Decide | Need follow up | 26_05_04 SteerCo.pptx | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
14 | NextGen | Complete | NextGen SteerCo | 2026-05-04 | Solar location for Buckeye | 13 | 2026-05-01 | 4:00 | 20 | Logan Jones | Kourtney Miller | Decide | Approved: Option 1 Carport + Zone 3 | 26_05_04 SteerCo.pptx | Adam Dunbar, Barat Smith, Zach Freeze, Karen Slatton
14 | NextGen | Complete | NextGen SteerCo | 2026-05-04 | Wallkill Next Steps | 13 | 2026-05-01 | 16:00 | 20 | Kourtney Miller | Kourtney Miller | Decide |  | 26_05_04 SteerCo.pptx
14 | NextGen | Complete | Offline | 2026-05-05 | Carnesville Pre-socialization w/ Latriece Watkins & Tom Ward | 14 | 2026-05-04 | 15:00 | 60 | Rob Montgomery, Jack Anderson, Karisa Spraque, Adam Dunbar, Matt C |  | Inform | Carnesville Pre-socialization | Carnesville May ASM | Latriece Watkins & Tom Ward
14 | NextGen | Scheduled | NextGen SteerCo | 2026-05-08 | Wallkill IRR & CapEx | 14 | 2026-05-07 | 16:00 | 45
15 | NextGen | Scheduled | MSM | 2026-05-12 | Carnesville Full Capital Ask | 14 | 2026-05-05 | 12:00 | 30 | Karisa Sprague | Kourtney Miller | Decide | Full approval for Carnesville | Carnesville May ASM | Dave Guggina
16 | NextGen | Scheduled | NextGen SteerCo | 2026-05-18 | Can we add TO/TMG to Wallkill | 15 | 2026-05-15 | 4:00PM | 30 | Andrew Skinkle | Andrew Skinkle | Decide |  |  | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
16 | NextGen | Scheduled | ASM | 2026-05-20 | Carnesville Full Capital Ask | 15 | 2026-05-12 | 12:00 | 30 | Karisa Sprague | Kourtney Miller | Decide | Full approval for Carnesville | Carnesville May ASM | Jon Furner
#N/A | NextGen | Pending Scheduling | Offline | TBD | Site Selection Date Scheduling - MCO, MSP, SEA, DEN | 13 | 2026-05-01 |  | 15 | Kourtney Miller | Kourtney Miller | Decide |  |  | Adam Dunbar
#N/A | NextGen | Pending Scheduling | Offline | TBD | CPC DD Approval for Wallkill & Buckeye | [5 empty] | Kourtney Miller | Decide |  |  | Ellen Sloneker, Phil Herr
#N/A | NextGen | Pending Scheduling | NextGen SteerCo | TBD | BDR for MSP, DEN, SEA Sign-off (Confirm path to 150M capacity ramp by FY) |  |  | 15:00 | 30 | Vijay Manoharan | Vijay Manoharan | Decide | BRR Approval for MSP, DEN, & SEA |  | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
#N/A | NextGen | Pending Scheduling | NextGen SteerCo | TBD | Preliminary IRR for PHX, MCO, MSP, DEN, SEA |  |  |  |  | Matt Termeer |  | Decide |  |  | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
#N/A | NextGen | Pending Scheduling | NextGen SteerCo | TBD | Reassess 450-mile centroid radius with impact to same day for MCO, MSP, DEN, SEA |  |  |  |  | Vijay Manoharan |  | Decide |  |  | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
#N/A | NextGen | Pending Scheduling | NextGen SteerCo | TBD | Review Market Model Coverage with peak and off-peak (Stores, Depots, NextGen Conventional FC) |  |  |  |  | Jack Anderson |  | Decide |  |  | Adam Dunbar, Vik Gopalakrishnan, Jack Anderson, John Clinton
#N/A | NextGen | Pending Scheduling | NextGen SteerCo | TBD | Van/Sedan Delivery Flow Follow-up |  |  |  | 30 | Advaith Venkataraman / Andrew | Advaith Venkataraman | Decide |  |  | Adam Dunbar, Jack Anderson
Formulas:
Turn-in Date = [Governance Date]-1
WW Turn-in Date = [Turn-in Date]

## NG Timelines
Program | NextGen | NextGen | NextGen | NextGen | NextGen | NextGen | NextGen
Node | Southeast | West | Northeast | Southeast | Upper Midwest | Mountain West | Pacific Northwest
Location | Carnesville, GA | Buckeye, AZ | Wallkill, NY | Orlando, FL | Minneapolis, MN | Denver, CO | Seattle, WA
State | GA | AZ | NY | FL | MN | CO | WA
FC Number | 4843 | TBD | 7028 | TBD | TBD | TBD | TBD
Airport Code | ATL5 | TBD | LGA1 | MCO? | MSP? | DEN? | SEA?
BDR Sign-off | 2025-09-23 | 2026-03-19 | 2026-03-19 | 2026-04-16 | 2026-04-23 | 2026-04-23 | 2026-04-23
Design and Construction
Due Diligence: Site Selection | 2025-05-15 | 2025-11-18 | 2025-11-18 | 2026-04-16 | 2026-04-16 | 2026-04-16 | 2026-04-16
Due Diligence 30% Work Ahead | 2025-05-15 | 2025-11-18 | 2025-07-22 | TBD | TBD | TBD | TBD
Due Diligence: 30% Design | 2025-07-17 | 2026-02-27 | 2025-12-02 | TBD | TBD | TBD | TBD
Due Diligence: 60% Design | 2025-11-10 | 2026-02-27 | 2026-02-27 | TBD | TBD | TBD | TBD
Due Diligence: 90% Design | 2025-11-10 | 2026-08-19 | 2026-05-22 | TBD | TBD | TBD | TBD
Due Diligence: CA Design | 2025-11-10 | 2026-08-19 | 2026-08-19 | TBD | TBD | TBD | TBD
Site Selected | 2025-05-23 | 2026-04-02 | 2025-10-22 | 2026-08-14 | 2026-08-14 | 2026-09-18 | 2026-09-18
Start of Design | 2025-07-21 | 2026-03-02 | 2025-12-01
30% Design Complete | 2025-10-28 | 2026-06-12 | 2026-02-27 | 2026-12-11 | 2026-09-04 | 2027-01-08 | 2027-01-08
30% ROM Pricing | 2025-11-21 | 2026-07-17 | 2026-04-03 | 2027-01-29 | 2027-01-29 | 2027-02-12 | 2027-02-12
60% Design Complete | 2026-03-06 | 2026-08-21 | 2026-05-29 | 2027-03-05 | 2027-03-05 | 2027-03-19 | 2027-03-19
60% ROM Pricing | 2026-04-10 | 2026-09-25 | 2026-07-03 | 2027-04-09 | 2027-04-09 | 2027-04-23 | 2027-04-23
90% Design Complete | 2026-05-01 | 2026-10-30 | 2026-08-07 | 2027-05-14 | 2027-05-14 | 2027-05-28 | 2027-05-28
Out to Permit | 2026-05-11 | 2027-01-04 | 2026-04-20 | 2027-05-24 | 2027-05-24 | 2027-06-07 | 2027-06-07
Permit Complete | 2026-08-14 | 2027-03-19 | 2028-01-28 | 2027-12-10 | 2027-12-10 | 2028-06-09 | 2028-06-09
Construction Start | 2026-09-07 | 2027-04-19 | 2028-02-28 | 2028-01-10 | 2028-01-10 | 2028-07-10 | 2028-07-10
Construction Substantial Completion | 2028-05-05 | 2028-12-15 | 2029-10-26 | 2029-09-14 | 2029-09-14 | 2030-03-01 | 2030-03-01
Phase 1 Go-live | 2028-10-30 | 2029-06-22 | 2030-05-12 | 2030-03-11 | 2030-03-11 | 2030-09-09 | 2030-09-09
Phase 2 Go-live | 2029-05-07 | 2029-12-03 | 2030-11-04 | 2030-09-02 | 2030-09-02 | 2031-03-10 | 2031-03-10
Go-Live FY | FY29 | FY30 | FY31 | FY31 | FY31 | FY31 | FY31
FY Capacity Added | FY29 | FY30 | FY31 | FY31 | FY31 | FY31 | FY31
Governance
Steer Co | 2026-03-26 | 2026-10-12 | 2026-07-06 | TBD | TBD | TBD | TBD
Vertical Start-Up | 2026-03-19 | 2026-10-22 | 2026-07-09 | TBD | TBD | TBD | TBD
SCDB Turn in | 2026-03-27 | 2026-10-23 | 2026-07-10 | TBD | TBD | TBD | TBD
SCDB | 2026-03-30 | 2026-10-26 | 2026-07-13 | TBD | TBD | TBD | TBD
RLM Turn-In | 2026-03-26 | 2026-10-14 | 2026-07-08 | TBD | TBD | TBD | TBD
RLM | 2026-04-02 | 2026-10-22 | 2026-07-14 | TBD | TBD | TBD | TBD
REC Turn-In | 2026-04-10 | 2026-10-28 | 2026-07-21 | TBD | TBD | TBD | TBD
REC | 2026-04-15 | 2026-11-04 | 2026-07-28 | TBD | TBD | TBD | TBD
CFO Turn-In | 2026-04-27 | 2026-11-15 | 2026-07-27 | TBD | TBD | TBD | TBD
CFO Review | 2026-05-04 | 2026-11-19 | 2026-08-03 | TBD | TBD | TBD | TBD
CPC Turn-In | 2026-05-05 | 2026-11-19 | 2026-08-04 | TBD | TBD | TBD | TBD
CPC | 2026-05-11 | 2026-12-02 | 2026-08-10 | TBD | TBD | TBD | TBD
MSM Turn-In | 2026-05-06
MSM | 2026-05-12
ASM Turn-In | 2026-05-12 | 2026-12-01 | 2026-08-11 | TBD | TBD | TBD | TBD
ASM | 2026-05-20 | 2026-12-10 | 2026-08-19 | 2027-06-17 | 2027-06-17 | 2027-07-15 | 2027-07-15
Engineering Design and Install
30 % Design - ENG | 2025-09-28 | 2026-05-13 | 2026-01-28 | 2026-11-11 | 2026-08-05 | 2026-12-09 | 2026-12-09
60% Design -ENG | 2026-02-04 | 2026-07-22 | 2026-04-29 | 2027-02-03 | 2027-02-03 | 2027-02-17 | 2027-02-17
90% Design - ENG | 2026-04-01 | 2026-09-30 | 2026-07-08 | 2027-04-14 | 2027-04-14 | 2027-04-28 | 2027-04-28
KNAPP Signed SOW | 2026-05-27 | 2026-12-17 | 2026-08-26 | 2027-06-24 | 2027-06-24 | 2027-07-22 | 2027-07-22
KNAPP start of Install (Start) | 2027-06-01 | 2028-01-22 | 2028-12-11 | 2028-10-10 | 2028-10-10 | 2029-04-10 | 2029-04-10
Phase 1 Commissioning - (Start) | TBD | TBD | TBD | TBD | TBD | TBD | TBD
FAT, End to End Testing, Financial Validation (Start) | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Additional Key Dates
Business Case Intake Open | 2026-03-16 | TBD | 2026-06-01 | TBD | TBD | TBD | TBD
Business Case Intake Closed | 2026-04-06 | TBD | 2026-06-15 | TBD | TBD | TBD | TBD
Business Case Complete | 2026-04-10 | TBD | 2026-07-03 | TBD | TBD | TBD | TBD
Incentives Secured | TBD | TBD | TBD | TBD | TBD | TBD | TBD
REC Dry Run | 2026-04-09 | TBD | TBD | TBD | TBD | TBD | TBD
CPC Dry Run | 2026-05-01 | TBD | TBD | TBD | TBD | TBD | TBD
ASM Dry Run | TBD | TBD | TBD | TBD | TBD | TBD | TBD
Moratorium Vote | N/A | N/A | 2026-05-28 | N/A | N/A | N/A | N/A
Site Selection Trip | 2025-05-23 | 2026-04-01 | 2025-11-22 | 2026-07-28 | 2026-08-25 | TBD | TBD
Talking Points & FAQ Updated | 2026-04-29 | TBD | TBD | TBD | TBD | TBD | TBD
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Not sure the exact date. BDR was redone after Aug ASM Rejection.
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $500K was loaded. The remaining $500K has not been approved
Note on F9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $500K was loaded. The remaining $500K has not been approved
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $500K was loaded. The remaining $500K has not been approved
Note on H9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: $500K was loaded. The remaining $500K has not been approved
Note on C12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Received partial 60% need remaining $784.5K that requires CPC approval by 6/26/26
Note on D13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Partial 90% approved. Need additional 417K requires CPC approval by 5/22/26
Note on F15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: At Risk due Karisa availability. Site Selection Trip not planned until 8/25
Note on D63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Got pulled from the agenda on 4/23/26 due to a legal not having the right signature. Pending Rescheduling
Notes.
- N/A will not show up on the Dashboard

## NG Budget
Project # | LX Number | SAP Project # | Building Type | Brief Scope of Work | Stage | FC Name | DC | Location | Node | Name |  | Budget | Actualized | Open Commits | Assigned | % of Assigned | Notes
17 | 90256.1000 | USDC-000297 | Next Gen | New Build | Pre-ASM | DOU | TBD | Doulas, MA | WMUS.SG.LOG.ASM | USDC-000297¦DOU¦TBD | 297 | 943000 | 73205 | 144708 | 217913 | 23.11% | On Hold
17 | 90235.1000 | USDC-000298 | Next Gen | New Build | Pre-ASM | ATL5 | 4844 | Carnesville, GA | WMUS.SG.LOG.ASM | USDC-000298¦ATL5¦4844 | 298 | 195514000 | 100633569 | 22153648 | 122787217 | 62.8% | Nov ASM Approved Budget Loaded
17 | 90367.1000 | USDC-000302 | Next Gen | New Build | Pre-ASM | LAS | TBD | Las Vegas, NV | WMUS.SG.LOG.EASM | USDC-000302¦LAS¦TBD | 302 | 2206000 | 1586608 | 174892 | 1761500 | 79.85% | On Hold
| 90536.1000 | USDC-000308 | Next Gen | New Build | Pre-ASM | LGA1 | 7028 | Wallkill, NY | WMUS.SG.LOG.EASM | USDC-000308¦LGA1¦7028 | 308 | 4700300 | 1364948 | 2190302 | 3555250 | 75.64%
| 90537.1000 | USDC-000309 | Next Gen | New Build | Pre-ASM | PHX3 | TBD | Buckeye, AZ | WMUS.SG.LOG.EASM | USDC-000309¦PHX3¦TBD | 309 | 5000000 | 0 | 2018000 | 2018000 | 40.36%
| 8654.1000 | USDC-000311 | Next Gen | New Build | Pre-ASM | DEN | TBD | Denver, CO | WMUS.SG.LOG.EASM | USDC-000311¦DEN¦TBD |  |  |  |  | 0 |  | Land bank not viable for NextGen
| 90591.1000 | USDC-000312 | Next Gen | New Build | Pre-ASM | MCO | TBD | Orlando, FL | WMUS.SG.LOG.EASM | USDC-000312¦MCO¦TBD |  | 500000 | 0 | 0 | 0 | 0% | 4/16: $500K funded for campus site selection
| 90593.1000 | USDC-000313 | Next Gen | New Build | Pre-ASM | SEA | TBD | Seattle, WA | WMUS.SG.LOG.EASM | USDC-000313¦SEA¦TBD |  | 500000 | 0 | 0 | 0 | 0% | 4/16: $500K funded for campus site selection
| 90592.1000 | USDC-000314 | Next Gen | New Build | Pre-ASM | MSP | TBD | Minneapolis, MN | WMUS.SG.LOG.EASM | USDC-000314¦MSP¦TBD |  | 500000 | 0 | 0 | 0 | 0% | 4/16: $500K funded for campus site selection
| 90915.1000 | USDC-000317 | Next Gen | New Build | Pre-ASM | DEN | TBD | Denver, CO | WMUS.SG.LOG.EASM | USDC-000317¦DEN¦TBD |  | 500000 | 0 | 0 | 0 | 0% | 4/16: $500K funded for campus site selection
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This USDC is for the Land Bank

## Automation Launch Dates
Scope | NextGen Greenfield | NextGen Aisle Expansion | NextGen Aisle Expansion | NextGen Aisle Expansion | NextGen Aisle Expansion | NextGen Greenfield | NextGen Greenfield | NextGen Greenfield | NextGen Greenfield | NextGen Greenfield | NextGen Greenfield | NextGen Greenfield | Non-Sort New Site | Non-Sort New Site | Non-Sort New Site | Non-Sort New Site | Non-Sort New Site | Non-Sort New Site | LAX2 ICC Expansion | IND1 ICC + Two-Tier
Sites | Stockton, CA | McCordsville, IN | Joliet, IL | Lancaster, TX | Green Castle, PA | Carnesville, GA | Buckeye, AZ | Wallkill, NY | Orlando, FL | Minneapolis, MN | Denver, CO | Seattle, WA | Pheonix, AZ | Charlotte, NC | Indianapolis, IN | Shoemakersville, PA | East Hartford, CT | Lebanon, OH | Chino, CA | Indianapolis, IN
Status | In Flight | In Flight | In Flight | In Flight | In Flight | May ASM | Dec ASM | Aug ASM | Due Diligence In Design | Due Diligence In Design | Due Diligence In Design | Due Diligence In Design | In Flight | In Flight | In Flight | August ASM | August ASM | August ASM | In Flight | In Flight
Phase 1 Go-live | 2026-08-24 | 2026-09-28 | 2026-09-08 | 2027-07-05 | 2024-06-14 | 10/30/28 (FY29) | 6/22/2029 (FY30) | 5/12/30 (FY31) | 11/19/29 (FY30) | 11/19/29 (FY30) | 5/13/30 (FY31) | 5/13/30 (FY31) | 4/20/2027 (FY28) | 5/20/2027 (FY28) | 4/20/2027 (FY28)
Phase 2 Go-live |  | 2027-07-28 | 2027-05-13 |  |  | 5/7/29 (FY30) | 12/3/2029 (FY30) | 11/4/30 (FY31) | 5/13/30 (FY31) | 5/13/30 (FY31) | 11/11/30 (FY31) | 11/11/30 (FY31)
Phase 1 Go-Live | FY27 3Q | FY27 3Q | FY27 3Q | FY28 2Q | FY28 2Q | FY29 3Q | FY30 Q2 | FY31 Q2 | FY31 Q1 | FY31 Q1 | FY31 Q3 | FY31 Q3 | FY28 Q1 | FY28 Q2 | FY28 Q1 | FY29 Q1 | FY29 Q1 | FY29 Q1 | FY27 Q3 | FY27 Q3
Phase 2 Go-Live | FY28 2Q | FY28 3Q | FY28 2Q |  |  | FY30 2Q | FY30 Q4 | FY31 Q4 | FY31 Q3 | FY31 Q3 | FY32 Q1 | FY32 Q1 | FY28 Q1 | [5 empty] | FY28 Q1 | FY28 Q2

## Info
Date | Walmart Week | Month | Quarter | Month | Quarter
2026-02-01 | 1 | Feb | 1 | Feb | 1
2026-02-02 | 1 | Mar | 1 | Mar
2026-02-03 | 1 | Apr | 1 | Apr
2026-02-04 | 1 | May | 2 | May | 2
2026-02-05 | 1 | Jun | 2 | Jun
2026-02-06 | 1 | Jul | 2 | Jul
2026-02-07 | 2 | Aug | 3 | Aug | 3
2026-02-08 | 2 | Sep | 3 | Sep
2026-02-09 | 2 | Oct | 3 | Oct
2026-02-10 | 2 | Nov | 4 | Nov | 4
2026-02-11 | 2 | Dec | 4 | Dec
2026-02-12 | 2 | Jan | 4 | Jan
2026-02-13 | 2
2026-02-14 | 3
2026-02-15 | 3
2026-02-16 | 3
2026-02-17 | 3
2026-02-18 | 3
2026-02-19 | 3
2026-02-20 | 3
2026-02-21 | 4
2026-02-22 | 4
2026-02-23 | 4
2026-02-24 | 4
2026-02-25 | 4
2026-02-26 | 4
2026-02-27 | 4
2026-02-28 | 5
2026-03-01 | 5
2026-03-02 | 5
2026-03-03 | 5
2026-03-04 | 5
2026-03-05 | 5
2026-03-06 | 5
2026-03-07 | 6
2026-03-08 | 6
2026-03-09 | 6
2026-03-10 | 6
2026-03-11 | 6
2026-03-12 | 6
2026-03-13 | 6
2026-03-14 | 7
2026-03-15 | 7
2026-03-16 | 7
2026-03-17 | 7
2026-03-18 | 7
2026-03-19 | 7
2026-03-20 | 7
2026-03-21 | 8
2026-03-22 | 8
2026-03-23 | 8
2026-03-24 | 8
2026-03-25 | 8
2026-03-26 | 8
2026-03-27 | 8
2026-03-28 | 9
2026-03-29 | 9
2026-03-30 | 9
2026-03-31 | 9
2026-04-01 | 9
2026-04-02 | 9
2026-04-03 | 9
2026-04-04 | 10
2026-04-05 | 10
2026-04-06 | 10
2026-04-07 | 10
2026-04-08 | 10
2026-04-09 | 10
2026-04-10 | 10
2026-04-11 | 11
2026-04-12 | 11
2026-04-13 | 11
2026-04-14 | 11
2026-04-15 | 11
2026-04-16 | 11
2026-04-17 | 11
2026-04-18 | 12
2026-04-19 | 12
2026-04-20 | 12
2026-04-21 | 12
2026-04-22 | 12
2026-04-23 | 12
2026-04-24 | 12
2026-04-25 | 13
2026-04-26 | 13
2026-04-27 | 13
2026-04-28 | 13
2026-04-29 | 13
2026-04-30 | 13
2026-05-01 | 13
2026-05-02 | 14
2026-05-03 | 14
2026-05-04 | 14
2026-05-05 | 14
2026-05-06 | 14
2026-05-07 | 14
2026-05-08 | 14
2026-05-09 | 15
2026-05-10 | 15
2026-05-11 | 15
2026-05-12 | 15
2026-05-13 | 15
2026-05-14 | 15
2026-05-15 | 15
2026-05-16 | 16
2026-05-17 | 16
2026-05-18 | 16
2026-05-19 | 16
2026-05-20 | 16
2026-05-21 | 16
2026-05-22 | 16
2026-05-23 | 17
2026-05-24 | 17
2026-05-25 | 17
2026-05-26 | 17
2026-05-27 | 17
2026-05-28 | 17
2026-05-29 | 17
2026-05-30 | 18
2026-05-31 | 18
2026-06-01 | 18
2026-06-02 | 18
2026-06-03 | 18
2026-06-04 | 18
2026-06-05 | 18
2026-06-06 | 19
2026-06-07 | 19
2026-06-08 | 19
2026-06-09 | 19
2026-06-10 | 19
2026-06-11 | 19
2026-06-12 | 19
2026-06-13 | 20
2026-06-14 | 20
2026-06-15 | 20
2026-06-16 | 20
2026-06-17 | 20
2026-06-18 | 20
2026-06-19 | 20
2026-06-20 | 21
2026-06-21 | 21
2026-06-22 | 21
2026-06-23 | 21
2026-06-24 | 21
2026-06-25 | 21
2026-06-26 | 21
2026-06-27 | 22
2026-06-28 | 22
2026-06-29 | 22
2026-06-30 | 22
2026-07-01 | 22
2026-07-02 | 22
2026-07-03 | 22
2026-07-04 | 23
2026-07-05 | 23
2026-07-06 | 23
2026-07-07 | 23
2026-07-08 | 23
2026-07-09 | 23
2026-07-10 | 23
2026-07-11 | 24
2026-07-12 | 24
2026-07-13 | 24
2026-07-14 | 24
2026-07-15 | 24
2026-07-16 | 24
2026-07-17 | 24
2026-07-18 | 25
2026-07-19 | 25
2026-07-20 | 25
2026-07-21 | 25
2026-07-22 | 25
2026-07-23 | 25
2026-07-24 | 25
2026-07-25 | 26
2026-07-26 | 26
2026-07-27 | 26
2026-07-28 | 26
2026-07-29 | 26
2026-07-30 | 26
2026-07-31 | 26
2026-08-01 | 27
2026-08-02 | 27
2026-08-03 | 27
2026-08-04 | 27
2026-08-05 | 27
2026-08-06 | 27
2026-08-07 | 27
2026-08-08 | 28
2026-08-09 | 28
2026-08-10 | 28
2026-08-11 | 28
2026-08-12 | 28
2026-08-13 | 28
2026-08-14 | 28
2026-08-15 | 29
2026-08-16 | 29
2026-08-17 | 29
2026-08-18 | 29
2026-08-19 | 29
2026-08-20 | 29
2026-08-21 | 29
2026-08-22 | 30
2026-08-23 | 30
2026-08-24 | 30
2026-08-25 | 30
2026-08-26 | 30
2026-08-27 | 30
2026-08-28 | 30
2026-08-29 | 31
2026-08-30 | 31
2026-08-31 | 31
2026-09-01 | 31
2026-09-02 | 31
2026-09-03 | 31
2026-09-04 | 31
2026-09-05 | 32
2026-09-06 | 32
2026-09-07 | 32
2026-09-08 | 32
2026-09-09 | 32
2026-09-10 | 32
2026-09-11 | 32
2026-09-12 | 33
2026-09-13 | 33
2026-09-14 | 33
2026-09-15 | 33
2026-09-16 | 33
2026-09-17 | 33
2026-09-18 | 33
2026-09-19 | 34
2026-09-20 | 34
2026-09-21 | 34
2026-09-22 | 34
2026-09-23 | 34
2026-09-24 | 34
2026-09-25 | 34
2026-09-26 | 35
2026-09-27 | 35
2026-09-28 | 35
2026-09-29 | 35
2026-09-30 | 35
2026-10-01 | 35
2026-10-02 | 35
2026-10-03 | 36
2026-10-04 | 36
2026-10-05 | 36
2026-10-06 | 36
2026-10-07 | 36
2026-10-08 | 36
2026-10-09 | 36
2026-10-10 | 37
2026-10-11 | 37
2026-10-12 | 37
2026-10-13 | 37
2026-10-14 | 37
2026-10-15 | 37
2026-10-16 | 37
2026-10-17 | 38
2026-10-18 | 38
2026-10-19 | 38
2026-10-20 | 38
2026-10-21 | 38
2026-10-22 | 38
2026-10-23 | 38
2026-10-24 | 39
2026-10-25 | 39
2026-10-26 | 39
2026-10-27 | 39
2026-10-28 | 39
2026-10-29 | 39
2026-10-30 | 39
2026-10-31 | 40
2026-11-01 | 40
2026-11-02 | 40
2026-11-03 | 40
2026-11-04 | 40
2026-11-05 | 40
2026-11-06 | 40
2026-11-07 | 41
2026-11-08 | 41
2026-11-09 | 41
2026-11-10 | 41
2026-11-11 | 41
2026-11-12 | 41
2026-11-13 | 41
2026-11-14 | 42
2026-11-15 | 42
2026-11-16 | 42
2026-11-17 | 42
2026-11-18 | 42
2026-11-19 | 42
2026-11-20 | 42
2026-11-21 | 43
2026-11-22 | 43
2026-11-23 | 43
2026-11-24 | 43
2026-11-25 | 43
2026-11-26 | 43
2026-11-27 | 43
2026-11-28 | 44
2026-11-29 | 44
2026-11-30 | 44
2026-12-01 | 44
2026-12-02 | 44
2026-12-03 | 44
2026-12-04 | 44
2026-12-05 | 45
2026-12-06 | 45
2026-12-07 | 45
2026-12-08 | 45
2026-12-09 | 45
2026-12-10 | 45
2026-12-11 | 45
2026-12-12 | 46
2026-12-13 | 46
2026-12-14 | 46
2026-12-15 | 46
2026-12-16 | 46
2026-12-17 | 46
2026-12-18 | 46
2026-12-19 | 47
2026-12-20 | 47
2026-12-21 | 47
2026-12-22 | 47
2026-12-23 | 47
2026-12-24 | 47
2026-12-25 | 47
2026-12-26 | 48
2026-12-27 | 48
2026-12-28 | 48
2026-12-29 | 48
2026-12-30 | 48
2026-12-31 | 48
2027-01-01 | 48
2027-01-02 | 49
2027-01-03 | 49
2027-01-04 | 49
2027-01-05 | 49
2027-01-06 | 49
2027-01-07 | 49
2027-01-08 | 49
2027-01-09 | 50
2027-01-10 | 50
2027-01-11 | 50
2027-01-12 | 50
2027-01-13 | 50
2027-01-14 | 50
2027-01-15 | 50
2027-01-16 | 51
2027-01-17 | 51
2027-01-18 | 51
2027-01-19 | 51
2027-01-20 | 51
2027-01-21 | 51
2027-01-22 | 51
2027-01-23 | 52
2027-01-24 | 52
2027-01-25 | 52
2027-01-26 | 52
2027-01-27 | 52
2027-01-28 | 52
2027-01-29 | 52
2027-01-30 | 53
2027-01-31 | 53