## Slide 1
Wallkill, NY | NextGen Fulfillment Center
Key Strategic Questions & Takeaways
Executive Decision Brief | Capital Commitment Review
KEY STRATEGIC QUESTIONS
Risk Tolerance
Are we aligned on the $65M-$200M incentive exposure and comfortable with the political path required to de-risk it?
Go-Live Timing
Can the business absorb a May FY31 go-live (shifted from Nov FY30) given network planning and demand forecasts?
Site Commitment
Do we confirm Wallkill as the preferred Northeast NextGen site, locking in the strategy and capital plan?
Political Strategy
Are we committed to 100% union construction labor as the primary lever to secure Governor support and protect incentives?
KEY TAKEAWAYS
Wallkill remains the preferred site
Superior network fit and overall value vs. all alternatives for the Northeast NextGen network.
A clear navigation path exists
Administrative moratorium exemption avoids the volatility of a public vote, keeping the decision with aligned officials.
Union labor is the political shield
100% union construction labor provides leverage with the Governor to secure both the exemption and incentive commitments.
Ask of Leadership:
Confirm commitment to Wallkill. Align on risk tolerance for $65M-$200M incentive exposure and a May FY31 go-live target.
PRIVATE AND CONFIDENTIAL | Walmart Internal Use Only
Wallkill NextGen FC | Executive Review | 2026

## Slide 2
* WALMART
Moratorium Navigation & Project Roadmap
We Have a Clear Path - And We're Already in Motion
Three strategic pillars de-risk the moratorium. The April 2026 exemption is the critical gate.
01 Administrative Exemption Route
Pursuing a direct Town exemption - not a public vote. This bypasses referendum volatility and keeps the decision with aligned officials, not an open ballot.
02 100% Union Labor as Political Shield
Committing to full union construction labor gives the project political legitimacy with the Governor - the key ally needed to secure both the moratorium exemption and $65M-$200M in discretionary incentives.
03 Legacy Project Framing (2003 Continuity)
Positioning Wallkill as a continuation of the 2003 approved project reduces environmental review triggers and infrastructure demands, lowering the bar for approval and accelerating the exemption pathway.
KEY MILESTONE ROADMAP | Critical Gate: April 24, 2026 Moratorium Exemption
Mar 25 2026
Town Supervisor Meeting
Mar 26 2026
Governor & Union Alignments
Apr 10-15 2026
Exemption Path Confirmed
Apr 24 2026
MORATORIUM EXEMPTION
! CRITICAL GATE
Aug 19 2026
ASM Full Capital Approval
2027
NYSDOT, SEQR & NYSDEC Approvals
2028
Site Work & Construction Start
May 2030
Phase 1 Go-Live
GO-LIVE
PRIVATE AND CONFIDENTIAL | Walmart Internal Use Only
Wallkill NextGen FC | Executive Review | 2026

## Slide 3
* WALMART
Critical Path Evaluation | Wallkill, NY vs. Douglas, MA
Douglas Does Not Move the Needle - Wallkill Remains the Right Choice
A ~6-week schedule difference is not a reason to abandon superior network fit and overall project value.
The Statutory Black Box:
Both sites face a mandatory, non-compressible 12-month environmental review. No capital injection or added labor can accelerate it - it is a fixed regulatory constraint that anchors both timelines equally.
FY30 Is Not Achievable at Either Site
Earliest go-live at either location is April-May 2030. The question is site selection, not timeline acceleration.
Milestone | Wallkill, NY (Preferred) | Douglas, MA (Alternative) | Schedule Delta
Fixed Site Dependency | May 26, 2026 - Town moratorium vote | Apr 1, 2026 - Design approval | ~8 wks
Environmental Submission | Oct 2, 2026 (SEQRA - NY) | Nov 30, 2026 (MEPA - MA) | Wallkill Earlier
12-Month Statutory Review | Fixed by law - cannot be accelerated | Fixed by law - cannot be accelerated | No Difference
Permitting Complete | Oct 2027 | Nov 2027 | Wallkill Earlier
Post-Permit Construction | ~20 months | ~20 months | No Difference
Substantial Completion | Oct 26, 2029 | Sep 7, 2029 | ~7 weeks
Phase 1 Go-Live Target | May 13, 2030 | Apr 1, 2030 | ~6 Weeks Only
Network Fit & Overall Value | Superior - Preferred Site | Lower value, higher CapEx | Wallkill Wins
Recommendation: Confirm Wallkill. Douglas offers only a ~6-week schedule advantage while delivering inferior network fit and higher capital cost. The 12-month statutory environmental review is identical at both sites and cannot be compressed. The schedule delta is not a sufficient reason to switch.
PRIVATE AND CONFIDENTIAL | Walmart Internal Use Only
Wallkill NextGen FC | Executive Review | 2026